v.1.0

MIlestone setting DOcument

For BIG Incubation Programme

# Milestone Setting Guidelines

As a next step, you are required to set 2 milestones for your start-up.

You may use the following guidelines for the start and completion dates when setting the milestones.

Start By: <incubation kick-off date>

- (Estimated incubation kick-off months are March for the January BIG intake, August for the May BIG intake and November for the September BIG intake)

Complete By: (for all milestones) should be within 6 to 8 months from the incubation kick-off date.

Some suggestions & samples are given below for your ready reference.

Please provide a minimum of:

- 1x product or technological development milestone

- 1x business development (BD) milestone

Samples provided here are for you reference, you may please customize it to meet your requirements and suitable for the start-up.

SAMPLES:

| Startup Name | Ambient Systems |
| --- | --- |
| Are you a Startup SG Founder Ivan Damnjanovic? | No |
| Cohort | Jan ‘22 |

| Priority |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Objective (Overarching goal) | Action (what are the steps that you’re planning to take to achieve this?) | Start by: (DD/MM/YY) | Complete by: (DD/MM/YY) |
| 1 | BD | Develop 3 use cases for the product through Proof-of-Concept (POC) Projects | Month 1: - Prepare list of local accounts (e.g., JTC, NUS, Changi Airport Group, CapitaLand, SMRT) - Identify relevant contacts and process to connect - Revise offering slide deck and propose POCs - Prepare [Team member] video Month 2: - Organize meetings and discussions - Draft POC agreement with prospective customers Month 3-6: - Work with stakeholders to implement the platform and model (e.g., connect data feeds via API or set-up localized gateway to aggregate site-level data from sensors, controls, and other sources) - Document outcomes and prepare case study | 01/03/2022 | 01/09/2022 |
| 2 | Product and Tech | Finalize Product Offering | - Adapt current UX / UI designs based on customer conversations - Refine the machine learning model using a combination of proprietary (collected), open-source, and simulated data - Look into IMDA accreditation and other standards - Develop cloud-based web app for users to access the outputs | 01/03/2022 | 30/04/2022 |
| 3 | Fundraising | Complete Pre-seed Round Fundraising ($300k USD) | - Finalize fundraising pitch deck - Send investment deck to personal network - Arrange calls and discussions - Organize investment agreements - Term sheets and investment agreements | 01/03/2022 | 30/04/2022 |

| Prepared & Signed by Startup Founders | Approved by IIE Representative (if applicable): | Approved / Endorsed by EiR: |
| --- | --- | --- |
| Name & Signature: Title: Date: | Name & Signature: Date: | Name & Signature: Date: |